## ProjectTeam
Name | GitHub Alias
Rey Phil | reyrp2
Grgic Pero | grgip1
Sultan Ghazal | sultg1
Magdub Fatma-Zahra | magdf1
Abu Baker Mootaas | abubm1
Oda Jemal | Odaoj1

## Product Backlog
ID | Story Name (User Story) | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Personal information | The user create an account and access to their personal data. The user can be flexible and change some of their given information |  | 50 | 0 | 0 | waiting
2 | Motivation | To keep the user motivated he/she loads a picture or types a text, which will remind him/her of his moitvation. To see if the user can buy some rewards for themselves, he/she checks how muchmoney they already saved |  | 60 | 0 | 0 | waiting
3 | Calendar | The user has a look on his personal calendar of the app and checks when he/she accomplished their daily goal and when not |  | 40 | 0 | 0 | waiting
4 | Making progress | To make sure that the user is progressing, the user changes his/her dialy goal every week and tries to reach his/her goal in an month |  | 30 | 0 | 0 | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | implement Person Class | The users can insert information about themselves |  | reyrp2 | grgip1 | medium | 6 |  |  | waiting
1.2 | 1 | Implement Person View | Implement the Vaadin View for the Person | Vaadin | magdf1 | Odaoj1 | medium | 4 |  |  | waiting
2.1 | 1 | Implement Motivation Class | Get the motivation picture from a local folder |  | grgip1 | abubm1 | medium | 7 |  |  | waiting
2.2 | 1 | Implement Motivator View | Implement the Vaadin View for the Motivator | Vaadin | sultg1 | magdf1 | high | 4 |  |  | waiting
3.1 | 1 | Implement Calendar Class | Implement Javacode which provid a montly calendar |  | abubm1 | sultg1 | low | 7 |  |  | waiting
3.2 | 1 | Implement Calendar View | Implement the Vaadin View for the Calendar monthly View | Vaadin | Odaoj1 | grgip1 | high | 4 |  |  | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2016-11-30 | 36 | 36