## ProjectTeam
Name | GitHub Alias
Rey Phil | reyrp2
Grgic Pero | grgip1
Sultan Ghazal | sultg1
Magdub Fatma-Zahra | magdf1
Abu Baker Mootaas | abubm1
Oda Jemal | Odaoj1

## Product Backlog
ID | Story Name (User Story) | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Personal information | The user create an account and access to their personal data. The user can be flexible and change some of their given information |  | 50 | 0 | 0 | waiting
2 | Keep motivated | The user can set an text which will keep him motivated |  | 10 |  |  | waiting
3 | Visual motivation | The user can load a picture which will motivate him |  | 30 |  |  | waiting
4 | Money motivation | The user can check the how much money he/she has already saved |  | 20 |  |  | waiting
5 | Calendar | The user has a look on his personal calendar of the app and checks when he/she accomplished their daily goal and when not |  | 40 | 0 | 0 | waiting
6 | Making progress | To make sure that the user is progressing, the user changes his/her dialy goal every week and tries to reach his/her goal in an month |  | 30 | 0 | 0 | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | implement Person Class | The users can insert information about themselves |  | Odaoj1 | grgip1 | medium | 6 |  | 6 | done
1.2 | 1 | implement Login View | The GUI where the User has log in with their e-mail and password |  | abubm1 | reyrp1 | low | 2 |  | 2 | done
1.3 | 1 | Implement Person View | Implement the Vaadin View for the Person | Vaadin | abubm1 | reyrp1 | medium | 4 |  | 4 | done
2.1 | 1 | Implement Motivator function of setting motivation text | the user can set an text for his motivation |  | grgip1 | magdf1 | medium | 2 |  | 2 | done
3.1 | 1 | Implement Motivator function of loading an picture | the user can load a picture from a local folder |  | grgip1 | magdf1 | high | 4 |  | 4 | done
3.2 | 1 | Setting color | set the collor based on the boolean |  | reyrp2 | grgip1 | low | 2 |  | 2 | working
3.3 | 1 | Implement Motivator View | Implement the Vaadin View for the Motivator | Vaadin | reyrp2 | sultg1 | high | 4 |  | 4 | done
5.1 | 1 | Implement Calendar Class | Implement Javacode which provid a montly calendar |  | magdf1 | odaoj1 | low | 6 |  | 6 | done
5.3 | 1 | Implement Calendar View | Implement the Vaadin View for the Calendar monthly View | Vaadin | sultg1 | abubm1 | high | 4 | 6 | 6 | done
1.1 | 2 | Checking Login | checks if the user and the password are correct and gives an respond |  | reyrp1 | odaoj1 | medium | 7 |  |  | working
1.2 | 2 | Connects the Person View with the Person Class | The GUI interacts with the Person class |  | abubm1 | sultg1 | high | 5 |  |  | working
1.3 | 2 | Implement Cigarettes class | will store information of the cigarettes which the user smokes |  | abubm1 | sultg1 | high | 4 |  |  | waiting
1.4 | 2 | Setting data base | preparing data base for saving user information |  | grgip1 | abubm1 | high | 7 |  |  | working
1.5 | 2 | General connection to DB | methode to connect/disconnect and get data from the DB
1.6 | 2 | Connecting Person class to data base | The class saves the user information into the data base |  | odaoj1 | grgip1 | high | 6 |  |  | waiting
2.1 | 2 | Connects Motivator View with the function of setting text | The GUI interacts with Motivator function |  | magdf1 | reyrp1 | medium | 4 |  |  | waiting
3.1 | 2 | Connects the Motivator View with the function of loading a picture | user can load picture over the GUI |  | sultg1 | odaoj1 | medium | 7 |  |  | working
3.2 | 2 | Connects the function of setting color with the Calendar View | the GUI interacts with the function of Motivator |  | odaoj1 | reyrp1 | low | 5 |  |  | working
4.1 | 2 | Implement Motivator function of getting the Saved Money | the motivator gets the saved money from the DB |  | reyrp1 | grgip1 | medium | 3 |  |  | waiting
4.2 | 2 | Implements CashRegister class | calculeates the saved money and stores in the DB |  | magdf1 | reyrp1 | high | 6 |  |  | working
4.4 | 2 | Implements Counter class | will store the count of smoked cigarettes |  | abubm1 | odaoj1 | high | 5 |  |  | waiting
4,5 | 2 | Connects Motivator View with the Counter class | the GUI interacts with the Coutner class |  | magdf1 | grgip1 | low | 4 |  |  | waiting
5.1 | 2 | Implement Goals class | stores the goals and the dialy goeals of the user |  | odaoj1 | abubm1 | medium | 3 | 2 | 2 | done
5.2 | 2 | Connects the Calendar View with the Calendar class | the GUI interacts with the Calendar Class |  | sultg1 | magdf1 | high | 7 |  |  | working
5.3 | 2 | GUI connection | connect all the GUIS togheter | Vaadin | reyrp1 | magdf1 | high | 4 | 6 | 6 | done

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2016-11-30 | 36 | 36
1 | 2016-12-06 | 24 | 22
1 | 2016-12-07 | 15 | 14
2 | 2016-12-08 | 84 | 84